## Dashboard
Start Pray ?????? |  |  |  | Release / Git
???? | 2026-03-14
|  |  |  | Current Branch | design/phase0-foundation
?? KPI |  |  |  | Current Commit | 9cb3b86
???? |  |  |  | Latest Tag | v2
??? |  |  |  | Snapshot Date | 2026-09-14 01:03:53
???
?? |  |  |  | Release KPI
????? |  |  |  | Total Releases
Active Releases
????? |  |  |  | Done Releases
Priority | Total | Done | Completion | Release Completion
P0
P1
P2
????
Domain | Total | Done | Completion
Frontend
Admin
前台優先小修版改造 + 安全/架構優化路線圖
Summary
你選擇的策略：先做前台體驗、第一階段只做小修補、後台先下架未完成頁，同時要清楚列出安全與架構優化路線。
盤點後的高風險不合理點（需納入路線）：
1. 客戶端可偽造登入身分（auth-storage.js、server-session.js）。
2. 公開 API 存在敏感資料外洩/越權風險（api/users/route.js、api/responses/[homeCardId]/route.js、api/home-cards/route.js）。
3. 前台樣式層過度膨脹與重疊（globals.css 約 7.6k 行，主題檔重複定義），影響美觀一致性與維護。
4. 後台資訊架構混雜真/假頁面（analytics/finance/moderation/support 為 mock），降低管理可信度。
5. API 存在舊版殘留與失配（/api/prayers*、/api/PrayerResponse、/api/home-cards/[id]）。
Implementation Changes
第一階段（前台小修補，2-3 週，先做）
1. 視覺一致性小修：統一首頁、祈禱牆、詳情頁的字級、留白、按鈕層級與卡片密度，不重做版型。
2. 內容豐富化小修：補強首頁「信任感區塊」與「引導區塊」文案層次，優化空狀態與錯誤提示。
3. 互動精修：減少首頁探索區過重的即時請求（保留功能但降載），優化載入中/無結果體驗。
4. 後台導航清理：先隱藏未完成 mock 模組，只保留已串接可運作頁面。
第二階段（安全與架構優化路線，並行設計、下階段落地）
5. Session 重構：改為 server 簽章/驗證 session（httpOnly），移除對可竄改 client cookie/localStorage 的信任。
6. Public API 收斂：下架或封鎖高風險舊 API（/api/users、/api/prayers*、/api/PrayerResponse），補上最小必要欄位 select。
7. 權限與資料流一致化：home-cards/responses 建立與修改改為 server 端用 session 決定 ownerId/responderId，不再吃前端傳入 ID。
8. Admin 邏輯一致化：每支 admin route 補顯式權限檢查（非僅依賴 middleware header），整理 banner 為單一資料來源。
介面/API 變更（先規劃）
9. POST /api/home-cards：移除 ownerId 請求欄位，由 server 注入。
10. POST /api/responses：移除 responderId 請求欄位，由 server 注入。
11. /api/responses/[homeCardId]：回傳 responder 白名單欄位（name/avatar），不回傳完整 user model。
12. /api/users、/api/prayers*、/api/PrayerResponse：標記淘汰並移除外部可用性。
Test Plan
1. 前台回歸：首頁、祈禱牆、詳情、登入/註冊、會員中心在 desktop/mobile 版面與互動檢查。
2. 安全驗證：手動竄改 pc-auth cookie/localStorage 後，不可讀寫他人資料；未登入不可建立卡片/回應。
3. API 合約：建立/查詢/檢舉/後台封鎖流程的成功與拒絕案例（401/403/422）要明確。
4. 建置品質：npm run lint、npm run build 必須無新增警告與無路由失配。
Assumptions
1. 第一階段不做全面重設計，只做「高感知小修補」。
2. 後台未完成頁面先隱藏，不在第一階段補齊全部功能。
3. 安全與架構路線本輪先定規格與優先級，實作安排在下一階段。
4. 不變更品牌核心定位與主要內容語言（維持現有中文主體）。

## Top_UX
ID | ?? | ???? | ??? | ??% | ???? | ???
UX-01 | 首屏主流程不清楚，使用者不知道第一步該做什麼 | `/prayfor` | P0 | 10 | 問題已確認，待版型重排 | 確定首屏只留 1 主 CTA + 1 次 CTA
UX-02 | 搜尋與卡片牆出現太晚，使用者要滑很久才進入主任務 | `/prayfor` | P0 | 10 | 問題已確認，尚未改版 | 將搜尋/熱門牆前移到 hero 後第一區塊
UX-03 | 登入/忘記密碼流程訊息矛盾，造成中斷感 | `/login` `/forgot-password` | P0 | 15 | 問題已確認，流程未修正 | 恢復 forgot-password 頁並更新登入頁文案
UX-04 | 詳情頁操作元素過多，主任務優先順序不清楚 | `/prayfor/[id]` | P0 | 10 | 問題已確認，互動未收斂 | 調整為「播放/回應/延伸瀏覽」三層 CTA
UX-05 | 手機版固定元件（header/播放器/浮動切換）互相搶空間 | `/prayfor` `/prayfor/[id]` | P1 | 10 | 問題已確認，待行動版重排 | 移除詳情頁浮動切換，播放器改 mini 模式
UX-06 | 後台手機版側欄與大表格可用性不足 | `/admin/*` | P1 | 10 | 問題已確認，尚未實作 | 補 mobile sidebar toggle 與表格行動版策略
UX-07 | 後台導覽與頁面真實性不一致（示意頁混在正式流程） | `/admin/*` | P0 | 20 | 已盤點哪些頁為示意資料 | 導覽拆分「正式可用 / 規劃中」
UX-08 | 後台操作回饋風格不一致（alert/confirm/inline 混用） | `/admin/*` | P1 | 10 | 問題已確認 | 定義統一 toast + confirm dialog 規範

## Tasks
Task ID | Domain | Task | Priority | Status | Progress% | Owner | Next Action | Source | Last Updated | Notes | Release | Git Version
TASK-001 | Frontend | 恢復 `/forgot-password` 實際頁面，不再 redirect 到 `/login` | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-002 | Frontend | 在登入頁加入明確的「忘記密碼？」入口 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-003 | Frontend | 移除登入頁錯誤文案「忘記密碼功能暫停中」 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-004 | Frontend | 統一網站品牌命名 `Start Pray / Prayer Coin / Let's Pray` | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-005 | Frontend | 修正首頁與導覽資訊架構，確認 `/` 的角色 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-006 | Frontend | 將首頁 CTA 全數導向有效且一致的產品流程 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-007 | Frontend | 將搜尋與熱門牆前移到首頁更前段的位置 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-008 | Frontend | 移除或補齊詳情頁 `關注` 按鈕功能 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-009 | Frontend | 下架未上線的安全承諾與功能描述 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-010 | Frontend | 重新定義詳情頁主 CTA 優先順序 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-011 | Admin | 後台登入改為伺服器端 session 驗證，不再只靠 `sessionStorage` | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-012 | Admin | 移除登入頁硬編碼 2FA 驗證碼（目前為固定值），改為真實 OTP 流程 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-013 | Admin | 所有 `/api/admin/*` 路由統一加上伺服器端權限檢查 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-014 | Admin | 禁止僅用 `x-admin-role` header 判斷權限（可被任意偽造） | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-015 | Admin | 修正高風險操作（封鎖/解封、交易狀態變更）的二次確認與操作回饋 | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-016 | Admin | 移除或明確標示尚未上線的示意頁（analytics / finance / moderation / support） | P0 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-017 | Frontend | 將首頁重新整理為 2 個主要 CTA + 3 條清楚主流程 | P1 | Done | 100 | Codex | Validate CTA conversion and scroll depth after release. | TODO0314 section 5 | 2026-03-14 | Prayfor landing rebuilt with 2 hero CTAs and 3 explicit entry flows. | R1-P1P2 | c85c8b0
TASK-018 | Frontend | 縮短 Hero 高度，首屏直接露出搜尋區或部分卡片 | P1 | Done | 100 | Codex | Collect mobile bounce-rate delta after deploy. | TODO0314 section 5 | 2026-03-14 | Hero height reduced for desktop/mobile to expose below-fold content earlier. | R1-P1P2 | c85c8b0
TASK-019 | Frontend | 把搜尋 debounce 從 2000ms 降到 300-500ms | P1 | Done | 100 | Codex | Monitor search metrics and typo tolerance tuning. | TODO0314 section 5 | 2026-03-14 | Debounce lowered to 450ms in HomePrayerExplorer. | R1-P1P2 | c85c8b0
TASK-020 | Frontend | 增加搜尋空狀態的導引與推薦分類 | P1 | Done | 100 | Codex | A/B test empty-state wording and click-through. | TODO0314 section 5 | 2026-03-14 | Added no-result guidance, fallback category chips, and popular wall shortcut. | R1-P1P2 | c85c8b0
TASK-021 | Frontend | 強化卡片資訊層級：標題、類別、回應數、最近更新 | P1 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-022 | Frontend | 簡化手機版詳情頁浮動元素 | P1 | Done | 100 | Codex | Validate mobile interaction on real devices. | TODO0314 section 5 | 2026-03-14 | Mobile floating prev/next arrows disabled; added inline previous/next cards block. | R1-P1P2 | c85c8b0
TASK-023 | Frontend | 將播放器改成低干擾 mini player 方案 | P1 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-024 | Frontend | 將會員中心改成分頁式或分段摘要式資訊架構 | P1 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-025 | Frontend | 清理 `/legacy` 圖片與舊連結依賴 | P1 | In Progress | 65 | Codex | Purge remaining /legacy image usage from non-critical pages. | TODO0314 section 5 | 2026-03-14 | Removed key legacy dependencies in site chrome/admin logos and prayfor landing. | R1-P1P2 | c85c8b0
TASK-026 | Frontend | 收斂 header 與 mobile override CSS | P1 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-027 | Frontend | 精簡註冊欄位，降低初次註冊負擔 | P1 | Done | 100 | Codex | Consider step-2 profile completion prompt in portal. | TODO0314 section 5 | 2026-03-14 | Faith/country changed to optional in signup form + API. | R1-P1P2 | c85c8b0
TASK-028 | Admin | 修復手機版側欄導覽（目前 CSS 有 `.is-open` 規則但缺少實際切換機制） | P1 | Done | 100 | Codex | Run device QA for focus trap/overlay close behavior. | TODO0314 section 5 | 2026-03-14 | Admin layout now has mobile sidebar toggle + backdrop + close-on-navigation. | R1-P1P2 | c85c8b0
TASK-029 | Admin | 將管理頁大表格改為可橫向滑動或卡片模式，避免手機版不可讀 | P1 | Done | 100 | Codex | Apply same table-wrap pattern to any new admin table module. | TODO0314 section 5 | 2026-03-14 | Introduced admin-table-wrap and applied to prayfor/prayerresponse/users/content tables. | R1-P1P2 | c85c8b0
TASK-030 | Admin | 合併 `/admin/content` 與 `/admin/marketing` 的 Banner 編輯來源，避免雙入口衝突 | P1 | Done | 100 | Codex | Remove stale links/references to old marketing editor in docs if any. | TODO0314 section 5 | 2026-03-14 | Admin marketing route now redirects to content; single banner editing source retained. | R1-P1P2 | c85c8b0
TASK-031 | Admin | 將搜尋改為明確 debounce（目前多頁為每次輸入即觸發查詢） | P1 | In Progress | 80 | Codex | Audit remaining admin pages with search to ensure debounce parity. | TODO0314 section 5 | 2026-03-14 | Added shared useDebouncedValue hook and applied on prayfor/prayerresponse/users filters. | R1-P1P2 | c85c8b0
TASK-032 | Admin | 統一後台文案與狀態字詞（中英混用、語氣不一致） | P1 | In Progress | 60 | Codex | Continue copy pass on secondary admin pages (log/settings/wallet alerts). | TODO0314 section 5 | 2026-03-14 | Admin login/layout and moderation status labels normalized to consistent Traditional Chinese wording. | R1-P1P2 | c85c8b0
TASK-033 | Admin | 將「存在路由但無導覽入口」的頁面整併到清楚資訊架構 | P1 | In Progress | 55 | Codex | Review remaining hidden admin routes and decide merge/remove strategy. | TODO0314 section 5 | 2026-03-14 | Added home-categories into admin nav and collapsed marketing editing entry via redirect. | R1-P1P2 | c85c8b0
TASK-034 | Frontend | 檢查鍵盤操作與閱讀器焦點流程 | P2 | In Progress | 35 | Codex | Run full keyboard-flow audit across header menu, player, comments, and admin tables. | TODO0314 section 5 | 2026-03-14 | Added aria-live regions and focus-visible styles for new search and action controls. | R1-P1P2 | c85c8b0
TASK-035 | Frontend | 補齊成功 / 錯誤 / 載入狀態的一致 UI | P2 | In Progress | 30 | Codex | Unify toast/inline status patterns across auth, detail, and admin actions. | TODO0314 section 5 | 2026-03-14 | Search/loading/empty states now expose consistent status semantics in explorer section. | R1-P1P2 | c85c8b0
TASK-036 | Frontend | 建立視覺設計 token 與元件規格 | P2 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-037 | Frontend | 補充 FAQ / 平台運作說明 / 聯絡方式 / 條款入口 | P2 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-038 | Admin | 建立後台設計規範（表單、表格、狀態、對話框、通知） | P2 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14
TASK-039 | Admin | 補齊 admin 操作審計可視化與異常警示（不只寫 log，還要可追蹤） | P2 | Not Started | 0 |  |  | TODO0314 section 5 | 2026-03-14

## Weekly_Log
Date | Summary | Completed Task IDs | Risks / Blockers | Next Week Plan | Owner
2026-03-14 | ??????
2026-03-14 08:39:41 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-14 08:39:50 | [AUTO] Push recorded: main @ c85c8b0 |  |  | Review release status and deployment result. | git-hook
2026-03-14 08:40:15 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-14 08:53:31 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-14 09:17:48 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-14 10:38:03 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-14 11:10:44 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-14 11:11:32 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-14 12:48:51 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-15 14:21:40 | [AUTO] Manual sync: main @ c85c8b0 |  |  | Update task status and release mapping. | git-hook
2026-03-21 15:20:22 | [AUTO] Commit recorded: main @ ea30eb9 |  |  | Continue task updates and prepare push. | git-hook
2026-03-21 15:53:04 | [AUTO] Commit recorded: main @ 9ac4d0b |  |  | Continue task updates and prepare push. | git-hook
2026-03-21 17:40:55 | [AUTO] Commit recorded: main @ 9d00e9c |  |  | Continue task updates and prepare push. | git-hook
2026-03-24 23:37:09 | [AUTO] Commit recorded: main @ d320697 |  |  | Continue task updates and prepare push. | git-hook
2026-03-25 00:09:02 | [AUTO] Commit recorded: main @ 0012f38 |  |  | Continue task updates and prepare push. | git-hook
2026-03-28 21:35:01 | [AUTO] Commit recorded: main @ 367b31a |  |  | Continue task updates and prepare push. | git-hook
2026-03-30 01:24:29 | [AUTO] Commit recorded: main @ 0091916 |  |  | Continue task updates and prepare push. | git-hook
2026-03-30 01:24:58 | [AUTO] Commit recorded: main @ 71c12b7 |  |  | Continue task updates and prepare push. | git-hook
2026-03-31 00:16:22 | [AUTO] Commit recorded: main @ 6ea34be |  |  | Continue task updates and prepare push. | git-hook
2026-04-02 23:17:07 | [AUTO] Commit recorded: main @ 8eeb610 |  |  | Continue task updates and prepare push. | git-hook
2026-04-26 12:57:49 | [AUTO] Commit recorded: main @ 7d71f48 |  |  | Continue task updates and prepare push. | git-hook
2026-04-26 13:09:29 | [AUTO] Commit recorded: main @ ce22e58 |  |  | Continue task updates and prepare push. | git-hook
2026-05-05 00:56:10 | [AUTO] Commit recorded: main @ d8dfbe6 |  |  | Continue task updates and prepare push. | git-hook
2026-05-09 20:01:08 | [AUTO] Commit recorded: main @ b034091 |  |  | Continue task updates and prepare push. | git-hook
2026-05-10 19:36:02 | [AUTO] Commit recorded: main @ c3a856b |  |  | Continue task updates and prepare push. | git-hook
2026-05-10 19:36:25 | [AUTO] Commit recorded: main @ dee4b64 |  |  | Continue task updates and prepare push. | git-hook
2026-05-12 23:39:45 | [AUTO] Commit recorded: main @ b6d027d |  |  | Continue task updates and prepare push. | git-hook
2026-05-23 12:03:01 | [AUTO] Commit recorded: main @ ae2e854 |  |  | Continue task updates and prepare push. | git-hook
2026-05-23 12:03:24 | [AUTO] Commit recorded: main @ fd5493d |  |  | Continue task updates and prepare push. | git-hook
2026-05-30 09:13:43 | [AUTO] Commit recorded: main @ 9d44c72 |  |  | Continue task updates and prepare push. | git-hook
2026-05-30 09:39:39 | [AUTO] Commit recorded: main @ 7aef01f |  |  | Continue task updates and prepare push. | git-hook
2026-05-30 09:42:51 | [AUTO] Commit recorded: main @ a27271e |  |  | Continue task updates and prepare push. | git-hook
2026-05-30 18:44:11 | [AUTO] Commit recorded: main @ aa29e0b |  |  | Continue task updates and prepare push. | git-hook
2026-05-30 18:44:48 | [AUTO] Commit recorded: main @ 2899667 |  |  | Continue task updates and prepare push. | git-hook
2026-05-30 18:57:53 | [AUTO] Commit recorded: main @ 457fe5d |  |  | Continue task updates and prepare push. | git-hook
2026-07-14 23:16:44 | [AUTO] Commit recorded: feature/roadmap-prd-implementation @ 753a726 |  |  | Continue task updates and prepare push. | git-hook
2026-07-14 23:45:50 | [AUTO] Commit recorded: feature/roadmap-prd-implementation @ 8068c33 |  |  | Continue task updates and prepare push. | git-hook
2026-07-15 00:07:16 | [AUTO] Commit recorded: main @ 89bcc02 |  |  | Continue task updates and prepare push. | git-hook
2026-07-15 00:18:28 | [AUTO] Commit recorded: main @ 694b927 |  |  | Continue task updates and prepare push. | git-hook
2026-08-04 00:25:11 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 6b8cc84 |  |  | Continue task updates and prepare push. | git-hook
2026-08-04 00:35:37 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 04538e7 |  |  | Continue task updates and prepare push. | git-hook
2026-08-04 01:49:17 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ a69ae05 |  |  | Continue task updates and prepare push. | git-hook
2026-08-04 01:56:23 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 4eaea7e |  |  | Continue task updates and prepare push. | git-hook
2026-08-04 02:02:04 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 78103e0 |  |  | Continue task updates and prepare push. | git-hook
2026-08-04 08:32:58 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 51b2ee4 |  |  | Continue task updates and prepare push. | git-hook
2026-08-04 23:01:03 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ ed43015 |  |  | Continue task updates and prepare push. | git-hook
2026-08-04 23:49:04 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ d485b04 |  |  | Continue task updates and prepare push. | git-hook
2026-08-05 00:57:50 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 4f13d72 |  |  | Continue task updates and prepare push. | git-hook
2026-08-05 21:35:54 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 70a6bb5 |  |  | Continue task updates and prepare push. | git-hook
2026-08-05 22:00:18 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ d0561ce |  |  | Continue task updates and prepare push. | git-hook
2026-08-05 22:05:02 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ c6b5b7d |  |  | Continue task updates and prepare push. | git-hook
2026-09-05 17:23:36 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 65961ab |  |  | Continue task updates and prepare push. | git-hook
2026-09-05 17:23:54 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 1f3c64f |  |  | Continue task updates and prepare push. | git-hook
2026-09-05 17:24:14 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ 2010830 |  |  | Continue task updates and prepare push. | git-hook
2026-09-05 17:24:38 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ d745f05 |  |  | Continue task updates and prepare push. | git-hook
2026-09-05 17:29:15 | [AUTO] Commit recorded: poc/minimal-prayer-redesign @ ab41479 |  |  | Continue task updates and prepare push. | git-hook
2026-09-07 00:49:09 | [AUTO] Commit recorded: fix/admin-visibility-and-voice-experience @ b63b440 |  |  | Continue task updates and prepare push. | git-hook
2026-09-07 00:49:36 | [AUTO] Commit recorded: fix/admin-visibility-and-voice-experience @ aa45cf8 |  |  | Continue task updates and prepare push. | git-hook
2026-09-07 00:50:01 | [AUTO] Commit recorded: fix/admin-visibility-and-voice-experience @ a289c51 |  |  | Continue task updates and prepare push. | git-hook
2026-09-07 00:50:12 | [AUTO] Commit recorded: fix/admin-visibility-and-voice-experience @ 4c52a82 |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 00:53:44 | [AUTO] Commit recorded: design/phase0-foundation @ 5b23f1f |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:03:36 | [AUTO] Commit recorded: design/phase0-foundation @ 32a60d6 |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:08:25 | [AUTO] Commit recorded: design/phase0-foundation @ 6364fd9 |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:09:28 | [AUTO] Commit recorded: design/phase0-foundation @ 56caee1 |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:18:02 | [AUTO] Commit recorded: design/phase0-foundation @ 4614b31 |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:21:46 | [AUTO] Commit recorded: design/phase0-foundation @ 74767fa |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:31:21 | [AUTO] Commit recorded: design/phase0-foundation @ b01c975 |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:39:55 | [AUTO] Commit recorded: design/phase0-foundation @ a22d0ff |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:41:49 | [AUTO] Commit recorded: design/phase0-foundation @ 372571e |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 01:45:30 | [AUTO] Commit recorded: design/phase0-foundation @ 869055a |  |  | Continue task updates and prepare push. | git-hook
2026-09-10 08:40:15 | [AUTO] Commit recorded: design/phase0-foundation @ 98c0023 |  |  | Continue task updates and prepare push. | git-hook
2026-09-11 20:58:33 | [AUTO] Commit recorded: design/phase0-foundation @ 1826857 |  |  | Continue task updates and prepare push. | git-hook
2026-09-11 21:39:06 | [AUTO] Commit recorded: design/phase0-foundation @ 4ba2705 |  |  | Continue task updates and prepare push. | git-hook
2026-09-11 21:39:07 | [AUTO] Commit recorded: design/phase0-foundation @ 232f031 |  |  | Continue task updates and prepare push. | git-hook
2026-09-11 21:39:59 | [AUTO] Commit recorded: design/phase0-foundation @ 338dea8 |  |  | Continue task updates and prepare push. | git-hook
2026-09-11 21:40:00 | [AUTO] Commit recorded: design/phase0-foundation @ e8f9c3b |  |  | Continue task updates and prepare push. | git-hook
2026-09-11 21:40:01 | [AUTO] Commit recorded: design/phase0-foundation @ 4216c36 |  |  | Continue task updates and prepare push. | git-hook
2026-09-12 14:44:50 | [AUTO] Commit recorded: design/phase0-foundation @ 1ab8502 |  |  | Continue task updates and prepare push. | git-hook
2026-09-12 14:44:55 | [AUTO] Commit recorded: design/phase0-foundation @ 6dd5e0b |  |  | Continue task updates and prepare push. | git-hook
2026-09-14 01:03:53 | [AUTO] Commit recorded: design/phase0-foundation @ 9cb3b86 |  |  | Continue task updates and prepare push. | git-hook

## Release_Tracker
Release ID | Release Name | Planned Date | Status | Scope | Owner | Start Git | Target Git | Actual Git | Notes
REL-2026-03 | UX Priority Batch | 2026-03-14 | Planned | Top UX + Admin UX |  |  |  | c85c8b0 | Initial tracking row

## Push_Log
Timestamp | Event | Branch | Commit | Tag | Commit Message | Remote | Refs
2026-03-14 08:39:41 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-14 08:39:50 | push | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git | refs/heads/main c85c8b0 refs/heads/main c85c8b0
2026-03-14 08:40:15 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-14 08:53:31 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-14 09:17:48 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-14 10:38:03 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-14 11:10:44 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-14 11:11:32 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-14 12:48:51 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-15 14:21:40 | manual | main | c85c8b0 | (no tag) | feat: improve player visibility, mobile UX, and zh copy | https://github.com/dan40912/prayer-coin.git
2026-03-21 15:20:22 | commit | main | ea30eb9 | (no tag) | chore: sync latest portal, player, and home updates | https://github.com/dan40912/prayer-coin.git
2026-03-21 15:53:04 | commit | main | 9ac4d0b | (no tag) | fix: restore logo path and harden prayer audio playback | https://github.com/dan40912/prayer-coin.git
2026-03-21 17:40:55 | commit | main | 9d00e9c | (no tag) | fix: stabilize prayfor audio and mobile header/player UI | https://github.com/dan40912/prayer-coin.git
2026-03-24 23:37:09 | commit | main | d320697 | (no tag) | feat(admin): roll out 2FA security hardening and console UX upgrades | https://github.com/dan40912/prayer-coin.git
2026-03-25 00:09:02 | commit | main | 0012f38 | (no tag) | feat: improve SEO metadata, footer spacing, and customer image upload flow | https://github.com/dan40912/prayer-coin.git
2026-03-28 21:35:01 | commit | main | 367b31a | (no tag) | release: v2.0.0 | https://github.com/dan40912/prayer-coin.git
2026-03-30 01:24:29 | commit | main | 0091916 | v2 | feat: finalize admin editors/player updates and add prod migration bundle | https://github.com/dan40912/prayer-coin.git
2026-03-30 01:24:58 | commit | main | 71c12b7 | v2 | chore: update progress tracker workbook | https://github.com/dan40912/prayer-coin.git
2026-03-31 00:16:22 | commit | main | 6ea34be | v2 | Fix global player replay diagnostics and loop behavior | https://github.com/dan40912/prayer-coin.git
2026-04-02 23:17:07 | commit | main | 8eeb610 | v2 | Remove legacy wireframe assets | https://github.com/dan40912/prayer-coin.git
2026-04-26 12:57:49 | commit | main | 7d71f48 | v2 | Add overcomer story media and SEO updates | https://github.com/dan40912/prayer-coin.git
2026-04-26 13:09:29 | commit | main | ce22e58 | v2 | Improve overcomer story recording modal | https://github.com/dan40912/prayer-coin.git
2026-05-05 00:56:10 | commit | main | d8dfbe6 | v2 | Add global prayer room experience and prayer seed tooling | https://github.com/dan40912/prayer-coin.git
2026-05-09 20:01:08 | commit | main | b034091 | v2 | Improve global prayer room map experience | https://github.com/dan40912/prayer-coin.git
2026-05-10 19:36:02 | commit | main | c3a856b | v2 | Update Start Pray docs and public UI | https://github.com/dan40912/Start-Pray.git
2026-05-10 19:36:25 | commit | main | dee4b64 | v2 | Update Start Pray docs and public UI | https://github.com/dan40912/Start-Pray.git
2026-05-12 23:39:45 | commit | main | b6d027d | v2 | Improve prayer sharing reports and guest posting | https://github.com/dan40912/Start-Pray.git
2026-05-23 12:03:01 | commit | main | ae2e854 | v2 | Improve public prayer experience | https://github.com/dan40912/Start-Pray.git
2026-05-23 12:03:24 | commit | main | fd5493d | v2 | Improve public prayer experience | https://github.com/dan40912/Start-Pray.git
2026-05-30 09:13:43 | commit | main | 9d44c72 | v2 | Improve localized prayer room experience | https://github.com/dan40912/Start-Pray.git
2026-05-30 09:39:39 | commit | main | 7aef01f | v2 | Stabilize homepage globe and prod deploy | https://github.com/dan40912/Start-Pray.git
2026-05-30 09:42:51 | commit | main | a27271e | v2 | Start global prayer room from Taiwan | https://github.com/dan40912/Start-Pray.git
2026-05-30 18:44:11 | commit | main | aa29e0b | v2 | Release Start Pray 2.1.0 | https://github.com/dan40912/Start-Pray.git
2026-05-30 18:44:48 | commit | main | 2899667 | v2 | Release Start Pray 2.1.0 | https://github.com/dan40912/Start-Pray.git
2026-05-30 18:57:53 | commit | main | 457fe5d | v2 | Stabilize global prayer room map loading | https://github.com/dan40912/Start-Pray.git
2026-07-14 23:16:44 | commit | feature/roadmap-prd-implementation | 753a726 | v2 | Implement roadmap PRDs and prayer experience updates | https://github.com/dan40912/Start-Pray.git
2026-07-14 23:45:50 | commit | feature/roadmap-prd-implementation | 8068c33 | v2 | Protect anonymous prayer response identities | https://github.com/dan40912/Start-Pray.git
2026-07-15 00:07:16 | commit | main | 89bcc02 | v2 | Merge feature/roadmap-prd-implementation into main | https://github.com/dan40912/Start-Pray.git
2026-07-15 00:18:28 | commit | main | 694b927 | v2 | Harden production database migration rollout | https://github.com/dan40912/Start-Pray.git
2026-08-04 00:25:11 | commit | poc/minimal-prayer-redesign | 6b8cc84 | v2 | refactor: simplify account and global navigation | https://github.com/dan40912/Start-Pray.git
2026-08-04 00:35:37 | commit | poc/minimal-prayer-redesign | 04538e7 | v2 | refactor: replace globe hero with minimal prayer entry | https://github.com/dan40912/Start-Pray.git
2026-08-04 01:49:17 | commit | poc/minimal-prayer-redesign | a69ae05 | v2 | feat: integrate prayer recording flow into homepage | https://github.com/dan40912/Start-Pray.git
2026-08-04 01:56:23 | commit | poc/minimal-prayer-redesign | 4eaea7e | v2 | docs: document current architecture and redesign progress | https://github.com/dan40912/Start-Pray.git
2026-08-04 02:02:04 | commit | poc/minimal-prayer-redesign | 78103e0 | v2 | docs: design anonymous prayer submission architecture | https://github.com/dan40912/Start-Pray.git
2026-08-04 08:32:58 | commit | poc/minimal-prayer-redesign | 51b2ee4 | v2 | feat: support anonymous prayer submission | https://github.com/dan40912/Start-Pray.git
2026-08-04 23:01:03 | commit | poc/minimal-prayer-redesign | ed43015 | v2 | refactor: present prayer needs as the homepage focus | https://github.com/dan40912/Start-Pray.git
2026-08-04 23:49:04 | commit | poc/minimal-prayer-redesign | d485b04 | v2 | feat: add prayer browsing and companion playback | https://github.com/dan40912/Start-Pray.git
2026-08-05 00:57:50 | commit | poc/minimal-prayer-redesign | 4f13d72 | v2 | refactor: unify anonymous prayer interactions across prayer pages | https://github.com/dan40912/Start-Pray.git
2026-08-05 21:35:54 | commit | poc/minimal-prayer-redesign | 70a6bb5 | v2 | feat: add anonymous prayed reactions | https://github.com/dan40912/Start-Pray.git
2026-08-05 22:00:18 | commit | poc/minimal-prayer-redesign | d0561ce | v2 | fix: harden prayer interaction flows | https://github.com/dan40912/Start-Pray.git
2026-08-05 22:05:02 | commit | poc/minimal-prayer-redesign | c6b5b7d | v2 | docs: complete final acceptance and release readiness review | https://github.com/dan40912/Start-Pray.git
2026-09-05 17:23:36 | commit | poc/minimal-prayer-redesign | 65961ab | v2 | @ refactor: use site logo for anonymous responder avatars | https://github.com/dan40912/Start-Pray.git
2026-09-05 17:23:54 | commit | poc/minimal-prayer-redesign | 1f3c64f | v2 | refactor: use site logo for anonymous responder avatars | https://github.com/dan40912/Start-Pray.git
2026-09-05 17:24:14 | commit | poc/minimal-prayer-redesign | 2010830 | v2 | feat: let card owners attach a 3-minute voice message | https://github.com/dan40912/Start-Pray.git
2026-09-05 17:24:38 | commit | poc/minimal-prayer-redesign | d745f05 | v2 | feat: rework the homepage hero and slim down font loading | https://github.com/dan40912/Start-Pray.git
2026-09-05 17:29:15 | commit | poc/minimal-prayer-redesign | ab41479 | v2 | docs: add PROD release plan for d745f05 | https://github.com/dan40912/Start-Pray.git
2026-09-07 00:49:09 | commit | fix/admin-visibility-and-voice-experience | b63b440 | v2 | fix(admin): repair search and show who is behind anonymous posts | https://github.com/dan40912/Start-Pray.git
2026-09-07 00:49:36 | commit | fix/admin-visibility-and-voice-experience | aa45cf8 | v2 | feat(web): bring back account entry points and rework the hero card | https://github.com/dan40912/Start-Pray.git
2026-09-07 00:50:01 | commit | fix/admin-visibility-and-voice-experience | a289c51 | v2 | feat(voice): offer text as well as voice, and make recordings audible | https://github.com/dan40912/Start-Pray.git
2026-09-07 00:50:12 | commit | fix/admin-visibility-and-voice-experience | 4c52a82 | v2 | docs: add a prompt for drafting text replies to unanswered cards | https://github.com/dan40912/Start-Pray.git
2026-09-10 00:53:44 | commit | design/phase0-foundation | 5b23f1f | v2 | refactor(design): collapse eight palettes into one token layer | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:03:36 | commit | design/phase0-foundation | 32a60d6 | v2 | fix(design): one accent, one vocabulary, one header height | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:08:25 | commit | design/phase0-foundation | 6364fd9 | v2 | refactor(design): share one card component, keep one CTA per screen | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:09:28 | commit | design/phase0-foundation | 56caee1 | v2 | docs: record what phase 0 landed and hand the rest to the three tracks | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:18:02 | commit | design/phase0-foundation | 4614b31 | v2 | fix(player): only show the player once someone presses play, and let them close it | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:21:46 | commit | design/phase0-foundation | 74767fa | v2 | fix(home,responses): stop the page contradicting itself, and let the replies read as people | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:31:21 | commit | design/phase0-foundation | b01c975 | v2 | feat(account): move the account flow onto the day surface, and lead with prayer | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:39:55 | commit | design/phase0-foundation | a22d0ff | v2 | feat(home): make the hero a deck you can actually flick through | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:41:49 | commit | design/phase0-foundation | 372571e | v2 | refactor(routes): the member area is /me, not /customer-portal | https://github.com/dan40912/Start-Pray.git
2026-09-10 01:45:30 | commit | design/phase0-foundation | 869055a | v2 | fix(prayer-room): stop the map controls stretching across the globe | https://github.com/dan40912/Start-Pray.git
2026-09-10 08:40:15 | commit | design/phase0-foundation | 98c0023 | v2 | fix(design): repairs found by testing the branch | https://github.com/dan40912/Start-Pray.git
2026-09-11 20:58:33 | commit | design/phase0-foundation | 1826857 | v2 | feat(recorder): move on to the next prayer three seconds after sending | https://github.com/dan40912/Start-Pray.git
2026-09-11 21:39:06 | commit | design/phase0-foundation | 4ba2705 | v2 | feat(terms,home): rewrite /terms around the upload rules, and bring the stats back | https://github.com/dan40912/Start-Pray.git
2026-09-11 21:39:07 | commit | design/phase0-foundation | 232f031 | v2 | fix(surface): keep <html data-surface> in sync on client-side navigation | https://github.com/dan40912/Start-Pray.git
2026-09-11 21:39:59 | commit | design/phase0-foundation | 338dea8 | v2 | refactor(player): fold the companion overlay into the one global player | https://github.com/dan40912/Start-Pray.git
2026-09-11 21:40:00 | commit | design/phase0-foundation | e8f9c3b | v2 | feat(nav): show the global prayer room entry again | https://github.com/dan40912/Start-Pray.git
2026-09-11 21:40:01 | commit | design/phase0-foundation | 4216c36 | v2 | chore: update progress tracker | https://github.com/dan40912/Start-Pray.git
2026-09-12 14:44:50 | commit | design/phase0-foundation | 1ab8502 | v2 | feat(home,prayfor): pick a spot on the globe, loop the hero, sort the wall | https://github.com/dan40912/Start-Pray.git
2026-09-12 14:44:55 | commit | design/phase0-foundation | 6dd5e0b | v2 | chore: update progress tracker | https://github.com/dan40912/Start-Pray.git
2026-09-14 01:03:53 | commit | design/phase0-foundation | 9cb3b86 | v2 | fix(voice): stop the countdown from restarting the recorder every second | https://github.com/dan40912/Start-Pray.git